MEMORANDUM

| TO | Chief Executive Officer ¦ Chief Financial Officer |
| --- | --- |
| FROM | R. Jegadeswari, Procurement & Finance |
| DATE | 23 March 2026 |
| RE | Vendor Spend Rationalisation — Findings & Recommendations |

VENDOR SPEND OVERVIEW

- 386 active vendors | Total LTM spend: $7.89M

- Breakdown: 265 vendors for Termination ($1.48M, 18.7%); 22 for Optimisation ($4.90M, 62.1%); 99 for Consolidation ($1.51M, 19.2%)

- Top 10 vendors account for 63.9% of total spend — acute concentration risk

TOP 3 OPPORTUNITIES

- Opportunities structured across Immediate and Parallel Strategic tracks to maximise speed, feasibility, and minimise operational risk

- Salesforce UK Contract Renegotiation (Immediate): right-size licences and secure multi-year pricing — est. $467,584

- Long-tail Vendor Termination Program (Parallel Strategic): cancel 265 Terminate-rated vendors, prioritising Score-1 SaaS first — est. $163,215

- Co-working & Office Space Consolidation: rationalise 8 vendors ($828K portfolio) to 1–2 preferred operators — est. $124,175

Total estimated savings: $754,974

ESTIMATED SAVINGS SUMMARY

- Total identified savings: $754,974 (9.6% of total LTM spend)

- Year 1 conservatively realisable: $453,000 (60% of identified savings)

- Payback on implementation effort: under 6 months

IMPLEMENTATION ROADMAP

- Month 1–2: Launch Salesforce renegotiation with procurement lead; activate 265-vendor termination program targeting Score-1 SaaS cancellations first

- Month 3–4: Continue vendor termination closures; issue co-working RFP and consolidate 8 operators to preferred panel of 1–2

- Month 4–6: Execute final Salesforce contract amendment; complete co-working consolidation and migrate headcount to retained locations

- Month 6+: Institutionalise quarterly vendor governance reviews; enforce category ownership to prevent tail-spend creep

RISKS AND MITIGATIONS

- Salesforce service disruption: Negotiate phased licence reduction with no-downtime SLA protection

- Departmental resistance to terminations: Engage budget owners early to pre-empt escalations

- Co-working lease break penalties: Review break clauses before issuing termination notices

RECOMMENDED NEXT STEP

Assign procurement lead to initiate Salesforce UK renegotiation by 30 April 2026, while simultaneously activating the 265-vendor termination program in Week 1 to capture quick-win savings in parallel.